## Sheet1
|  | Bussiness structure | 60% | 1260 | 1320
|  | Press kit | 10% | 210 | 220
|  | Marketing plan | 30% | 630 | 660
|  |  |  | 2100 | 2200
order | who
|  |  | Start | Length | Gap | Length | Gap | Length
1 | 1 | Setup Company | 0 | 4
2 | 2 | Game Ideas and Research | 3 | 28
3 | 2 | Art asset sketches | 3 | 14
4 | 2 | Design Wireframe | 10 | 10
5 | 2 | Final Art Sketches | 21 | 7
6 | 3 | Create 2 min pitch for UK game fund | 21 | 7
7 | 1 | GOV and UK Games loan: apply | 25 | 25
8 | 1 | Receive Loans | 50 | 2 | 20 | 2
9 | 1 | Purchase Hardware | 53 | 5
10 | 1 | Purchase Software | 53 | 3
11 | 3 | Create Character assets | 35 | 21 | 31 | 21 | 31 | 21
12 | 2 | Create and Publish first Press Kit | 36 | 14
13 | 2 | Aquire feedback from Public | 56 | 21 | 40 | 21 | 70 | 21
14 | 3 | Create and Post 30 second gameplay videos on Social Media | 68 | 10
15 | 1 | Aquire Target Market/Audience | 80 | 10
16 | 1 | Become Partners with Play Dead Studios | 88 | 6
17 | 3 | Create game HUD's | 83 | 14
18 | 1 | Edit Press kit accessable to the public | 125 | 5
19 | 3 | Polish character assets | 160 | 14
20 | 2 | Create character animations | 175 | 7 | 14 | 14
21 | 2 | Research Potential environmental assets | 180 | 7
22 | 3 | Sketch environmental assets | 185 | 14
23 | 3 | Create environmental assets | 220 | 5
24 | 1 | Add enviromental assets to press kits online | 226 | 4
25 | 4 | Player character interactes with enviroment | 220 | 35
26 | 5 | Player HUD's interact with code | 250 | 14
27 | 5 | Create first build | 280 | 4
28 | 1 | Gain feedback from game build | 268 | 14
29 | 4 | Improve and polish game build | 275 | 7 | 7 | 7
30 | 1 | Create and Publish teaser trailer | 290 | 7
31 | 1 | Publish game pre-orders on target platforms | 300 | 60
32 | 4 | Create and publish Game Demos | 305 | 14
33 | 1 | Receive feedback from demos | 310 | 14
34 | 4 | Polish game programming | 317 | 7
35 | 3 | Create and Publish Cinematic trailer | 324 | 6
36 | 1 | Advertise Offical Release date to Public | 330 | 30
37 | 1 | Release game to the public | 359 | 7